#### RMP Steering Committee Meeting

November 3rd, 2010

San Francisco Estuary Institute

Second Floor Conference Room

7770 Pardee Lane, Oakland, CA

1:00 PM - 3:30 PM

DRAFT MINUTES

Members Present:

Dave Allen, USS POSCO

Steve Bauman, Mirant

Kevin Buchan, WSPA

Ellen Johnck, Bay Planning Coalition

Tom Mumley, SFB RWQCB

Karin North, City of Palo Alto (alternate for Brad Eggleston)

Adam Olivieri, EOA/ BASMAA

Kirsten Struve, City of San Jose

Dan Tafolla, Vallejo Sanitation and Flood Control District

Others Present:

Rachel Allen, SFEI

Mike Connor, EBDA

Jay Davis, SFEI

Rainer Hoenicke, SFEI

Lawrence Leung, SFEI

Trish Mulvey, SFEI Board of Directors

Meg Sedlak, SFEI

Ian Wren, Baykeeper

- Approval of Agenda and Minutes

Meg Sedlak reviewed action items from the previous Steering Committee (SC) meetings.  She noted that she and Lawrence Leung had had a productive meeting with Adam Olivieri and Trish Mulvey about the accounting terms used in the RMP budget summary; Lawrence indicated that he had incorporated the recommendations from that discussion in the current memo.  Ms. Sedlak and Mr. Leung also looked into developing an option for rolling average metal loads for the POTWs, however they concluded that it would not save on time or effort, and according to some BACWA members, the current method does provide valuable information for trends.  Mike Connor noted that based on the information provided by RMP, EBDA and EBMUD determined that they had been over-reporting chromium data.

Trish Mulvey asked that the action item table from the minutes be compiled and distributed as a separate document.  Adam Olivieri motioned to approve the minutes, and Dan Tafolla seconded it.  The minutes were approved unanimously.

Action items:

- Include the action item table as a separate document.

- Committee Member Updates

There were no committee member updates.

- Technical Review Committee Meeting Summary

At the September Technical Review Committee (TRC) meeting, the group discussed the possibilities for the analysis of sediment samples for dioxins, the funds for which the SC approved in the May SC meeting.  The TRC recommended analyzing a combination of wet season and dry season samples.  Also of note, the TRC discussed the sampling technique for pesticide analysis in water, and recommended collecting whole water samples rather than using the resin columns.

Jay Davis mentioned that he will distribute to the SC a scope for fact sheets, and the draft of the triclosan and triclocarban factsheet.  Kirsten Struve mentioned that there is already a triclosan fact sheet.  Karin North confirmed this, but mentioned that it was created in 2003, and that it does not explain the science, which the RMP version will.  Jay Davis added that it will also provide links to relevant data.

Action items:

- Distribute fact sheet scope and draft triclosan and triclocarban fact sheets to the SC.

- 2010 Budget Status

Lawrence Leung reviewed the status of the budget, noting that it is on track for 2010.  Paradise Cay is continuing to pay off its fees in incremental amounts.  The balance from the 2005-2007 fees owed by Caltrans should be received shortly, and the 2010 fees will be received next October upon completion of deliverables (Pulse and Annual Meeting).

Adam Olivieri asked if Lawrence Leung follows up on bills and invoices, such as Paradise Cay.  Lawrence Leung confirmed that he routinely calls to remind the organizations.  Tom Mumley asked that the RMP move towards paperless billing practices.  Mike Connor suggested that a web-based spreadsheet would facilitate the submission of the POTW annual loading data.

The RMP is aiming to maintain a reserve of about $200,000.  Tom Mumley noted that including the expected Caltrans fees, the reserve is currently over $300,000.

Meg Sedlak indicated that as a result of cost-saving measures that the 2010 subcontractor budget has approximately $16,000 that is unallocated.  She requested that approximately $15,000 be reallocated to retain a consultant, Craig Jones, to complete the Margins Conceptual Model project.  This project was delayed in part due to the departure of John Oram in June of 2010.

Tom Mumley noted that while he agrees that this project is a priority, in the future he would like to see a prioritization of unfunded projects, to determine where suddenly available funds such as these could be spent most effectively.  Kevin Buchan and Dan Tafolla agreed that such a prioritization would be helpful.  Meg Sedlak indicated that she prefers to have all projects go through the normal process of funding, and that she reserves these special requests for projects that encounter unexpected setbacks or for time-sensitive opportunities such as 2010’s NOAA Mussel Watch collaboration.

Tom Mumley also indicated that the December 2010 deadline can be extended to January 2011 if it will improve the final product.  Meg Sedlak noted that the current schedule is for a first draft in December, with review in January.

Kevin Buchan recommended approval of the reallocation of subcontractor funds.  Tom Mumley seconded it, the funding was approved.

Action items:

- Move towards using paperless billing practices for WWTP invoices and data submission.

- Allocate $15,000 to Craig Jones for lead-authoring the Margins Conceptual Model report.

- Approval of 2011 Draft Program Plan/ Budget

Meg Sedlak noted that the new planning agenda has moved approval of the budget up one quarter to the October meeting.  In October 2010, with regard to participant fees, the SC did not approve an increase in fees for 2012; fees will remain the same as 2011.  There is an $11,471 shortfall from dredgers.  There was a surplus in dredger funds in 2010, so staff is requesting the use of these funds to cover the $11,471 shortfall in 2011.

The projected revenue from interest for 2011 is low.  SFEI had estimated that the revenue from interest would be $25,000.  At this time, we estimate only $15,000.  Consequently, Ms. Sedlak requested an additional $10,000 to cover the shortfall in interest.  She also requested $52,000 for analysis of dioxin samples, which had been deferred (a memo was included in the agenda package on this).

In reviewing the 2011 Expenses spreadsheet, Tom Mumley asked for a clarification of “Other Direct Costs”.  Meg Sedlak noted that expenses such as printing the Pulse, annual meeting costs, honorariums for panel members, equipment such as rain jackets, and the financial audit are all included in this category.

Tom Mumley noted that he found the style of the Program Plan wordy, and asked for clarification of the intended audience.  Meg Sedlak clarified that it is a general summary intended for the SC, with details included in the companion document: the detailed workplan, reviewed annually by the TRC.  Tom Mumley suggested that the Program Plan be written with the “punch line” at the beginning, with rationale following.  Kirsten Struve suggested that the hierarchy of documents be more clearly laid out.

Tom Mumley asked for a one-page summary of the RMP Program Plan, based on the budget summary on the last page of the Program Plan.  Karin North suggested that this one page document could also lay out the document hierarchy and provide appropriate links to more detailed sources of information.

Adam Olivieri commented that it would be useful to have a separate budget summary table that was annotated with descriptions of each of the items.  Karin North suggested using an 11 by 17 inch paper to get all of the information on one page.  She also noted that if it is posted on the web, it could be linked to more detailed descriptions.

Tom Mumley also asked how comments from the TRC get incorporated into proposals for the projects, and where the predicted product from the projects is stated.  Jay Davis noted that the revised proposals are included in the scopes of work as part of the contracts.

Tom Mumley asked whether the special studies are posted on the web and Jay Davis indicated that the Detailed Workplan includes a summary of the study ideas.   It was suggested that the RMP post the studies on the web.  Adam Olivieri commented that there are really three documents: the Program Plan, the budget and the Detailed Workplan and that each needs to reference the other two documents.

Mike Connor noted that all parties agreed that the copper and salmon study would meet the TMDL requirement, and Tom Mumley concurred.  Adam Olivieri asked if the funding requests (dioxin funds, reserve interest, and dredger shortfall) were needed in order for the RMP to operate.  Meg Sedlak noted that the dioxins study could be deferred another year but that the $20,000 from interest and dredger shortfall are necessary.  Tom Mumley motioned to approve the Program Plan, with the modifications, which Adam Olivieri seconded.  The Program Plan was approved.

Action items:

- Aggregate funded special studies and make them available on the website.

- Make the recommended clarifications and corrections to the Program Plan.

- Approval of 2011 Master Plan and Decision on 2012 Fees

Jay Davis outlined the format and improvements in the Master Plan, including an update of Figure 2.  He stated that approximately 40% of funds go to program management, and the further breakdown of allocation of funds is laid out in the Master Plan.  If the stakeholder fees remain fixed, there will be a shortage in funds resulting in less work (i.e., funding for special studies would decrease).  Because of municipal and other agencies’ financial planning cycles, the SC will need to decide on the fees for 2012 during this meeting so the agencies can budget appropriately.

Tom Mumley lauded the Master Plan, mentioning that it gives a sense of what the RMP is doing.  Assuming that the fees are not increased, there will be a substantial shortfall in funds for Special Studies in 2012.  Jay Davis noted that Meg Sedlak will flesh out the Status and Trends Five-year plan in the first quarter of 2011.

Jay Davis circulated a handout outlining budget scenarios for Special Studies in the upcoming years based on various increases in RMP fees, SFEI labor, and subcontractor rates.  Ideally, fees would keep pace with salary increases, and the Program would not have to shrink.  Rainer Hoenicke noted that since fee increases have not kept pace with inflation there has effectively been a decline in RMP funds since 2005.  He added that SFEI salary structure is currently about 30% lower than the salary classes in comparable agencies, such as EBMUD and SFPUC.  As an organization, SFEI needs to ensure that it does not lose staff because of the salary discrepancy.  He therefore urged the SC to consider a scenario where the RMP fees do not remain flat.

Kevin Buchan supported the SFEI decision to adjust its salaries as necessary.  However, he indicated, as did Adam Olivieri, that it is currently not possible to increase RMP fees.  Tom Mumley asked the overarching question of “what do we want the RMP to do?”.  If required, the Water Board could start using regulatory measures to maintain the scope of work of the RMP.

Dan Tafolla asked if the agencies could make up fee increases at a later date.

Adam Olivieri stated that if the RMP was operating with a smaller budget perhaps some items could be deferred or performed less frequently, such as producing the Pulse once every two years.  Trish Mulvey suggested that the Status and Trends monitoring could be performed every other year.  Tom Mumley suggested that studies such as small tributary loading studies need not be performed with RMP funds if the program were pressed for resources, as it does not benefit all of its member organizations.  However, this would require the stormwater agencies to meet the regulatory requirement through other programs/entities, and may not be as economically efficient as conducting this work through the RMP.

Tom Mumley summarized the general consensus: that the agencies cannot approve a fee increase for 2012.  However, Ian Wren and Adam Olivieri suggested that RMP staff lay out the consequences of a decrease in special studies funding by prioritizing projects and determining which are required.  This will be taken into account at the Master Planning workshop, along with issues such as Jim Cloern’s retirement from the USGS and the potential loss of water quality monitoring that is currently conducted by that group.  Kevin Buchan suggested that RMP studies that benefit specific groups would be the first to be cut, while Adam Olivieri considers the first priority of the RMP to be permit compliance.  Rainer Hoenicke suggested that this discussion be outlined by Meg Sedlak and Jay Davis and included in the agenda for the planning workshop.

Regarding additional resources, Rainer Hoenicke suggested that the SC discuss working with Judy Kelly to get additional funds, such as USEPA funds, at a later meeting.  Tom Mumley noted that there has been no concrete progress with regards to SEP funds; however, if the RMP has a list of project needs identified, then they could potentially use SEP money to fund some of them.  Tom Mumley also noted that future USEPA funding may be limited to restoration efforts. Trish Mulvey asked about program review; however the group felt that this was low on the list of priorities.  This topic can be addressed in the planning workshop.

The group concluded that the Program would not increase fees in 2012.  Mike Connor pointed out that this decision reflects “what we want the RMP to be”, because the same level of funding will necessarily make possible less work as the years go on.  He suggested that the SC could decide now to make up the deficit by increasing fees 6% in 2013.  In the meantime, each of the stakeholders should prioritize RMP activities and identify areas where there could be cuts.  Kevin Buchan motioned for a 0% increase in fees for 2012, which Ellen Johnck and Kirsten Struve seconded.  The motion was approved.

Ellen Johnck motioned to endorse the Master Plan.  Kevin Buchan seconded the motion, and the SC voted unanimously to endorse the Master Plan.

Kevin Buchan noted that the Master Plan should remain an internal document and not be distributed beyond the SC.  RMP staff will use a web-based tool to schedule the Master Planning Workshop for February 2011.

Action items:

- Each stakeholder group to consider RMP project prioritization in preparation for the Planning Workshop.

- Include a program review as a potential task for 2012 at the Planning Workshop.

- Schedule the Master Planning workshop for a date in February 2011.

- Dredger Fees for 2011 to 2013

Meg Sedlak and Lawrence Leung proposed to set up a separate account to help mitigate the variability in funds received from dredgers, which arises as a result of the fluctuation in the amount of material dredged within any one given year.  Lawrence Leung proposed saving any dredger surplus in a separate account to offset the years in which there are dredger shortfalls.

Lawrence Leung explained that the fees would remain the same for 2011-2013 period.  As part of the dredger fee system approved in 2007, the rolling average for dredger volumes for the Annual dredgers (the top five) is recalculated every three years.  The fee rate for 2011-2013 will be $0.60 per cubic yard of disposed material.  Lawrence Leung indicated that if the new volumes resulted in surpluses for a number of years, the SC could revise the rate.

Ellen Johnck noted that with the implementation of the LTMS, the amount of material being deposited in the Bay is decreasing.  She supported the plan of a separate account.

Tom Mumley motioned to approve the letter to the dredgers, notifying them of the dredger fee rates and revised bin volumes.  Adam Olivieri seconded the motion, and the motion passed unanimously.

- Annual Meeting and Pulse

Jay Davis relayed the TRC recommendation for the theme of the 2011 Pulse to the SC: “effects of contaminants on aquatic life in the Bay”.  This would also be the theme for the Annual Meeting.  He noted that it is well-timed with a forthcoming summary on the Exposure and Effects Pilot Study.

Tom Mumley asked if there was enough good material to produce a Pulse on this topic, but also noted that the RMP has never had trouble developing an interesting day long meeting.

Jay Davis added that the effects articles would cover benthos, birds, and fish, and would require collaboration from a number of different researchers.  The deadline for draft articles this year will be March.  Karin North added that Janet Thompson, of USGS, did a benthos study at Palo Alto, which could be included.

The group approved the topic of “effects of contaminants on aquatic life in the Bay” for the 2011 Pulse and Annual Meeting.

Meg Sedlak gave a recap on the 2010 Annual Meeting, which notably had lower attendance than previous years, with only 160 attendees.  The survey only had 20 respondents which is not very representative.  Kevin Buchan noted that it is generally very difficult to get feedback from participants.  Karin North noted that the Bay Area Pollution Prevention Group had noted that the meeting was stormwater centric, and therefore chose not to attend.  Tom Mumley suggested that the decrease in attendance was likely more linked with the economy than with the chosen topic.

With regards to incorporating the RMP meeting as a day in the State of the Estuary (SOE) Conference, Tom Mumley noted that the SOE may be only a two-day meeting, and that including the RMP as part of it may require that the RMP purchase a day at the Marriott Convention Center.

Jay Davis asked if the RMP should hold another Mercury Meeting this year, or potentially have a meeting on another topic.  Tom Mumley noted that the Annual Mercury Meetings have been helpful and successful; however it does not seem to be necessary for 2011.

Action items:

- Look into including the RMP Annual Meeting in the SOE conference.

- Include the feedback on communication formats from the RMP Annual Meeting at the next SC meeting.

- Plus/Delta on today’s meeting

The next SC meeting will be held on January 19, 2011.  An on-line poll will be set up to determine the date of the next Master Planning workshop.

Ellen Johnck announced that she is leaving the Bay Planning Coalition, and that December 31st is her last day as Executive Director.  She will remain in contact with the organization as a consultant, and will help the new Executive Director with her role on the SC.

| # | Action Items – November 2010 | Who? | When? | Status 1/11/2011 |
| --- | --- | --- | --- | --- |
| 1 | Distribute factsheet scope and draft Triclosan and Triclocarban factsheets to the SC | Jay Davis | First quarter 2011 | Pending. To be addressed in first quarter 2011 |
| 2 | Allocate $15,000 to Craig Jones for lead-authoring the Margins Conceptual Model report | Meg Sedlak | November 2011 | Done |
| 3 | Develop website tool for uploading of WWTP metal loads | Meg Sedlak | December 22nd | IT team is working on a site for the 2011 invoicing. |
| 4 | Update the RMP 2011 Program Plan based on feedback | Meg Sedlak | By December 1 | Posted on web-site |
| 5 | Each stakeholder group to consider RMP project prioritization in preparation for the Planning Workshop | RMP stakeholders | By January 19th, 2011 |  |
| 6 | Send out a Doodle poll for the SC planning workshop | Rachel Allen | Completed. | Date set for February 7th. |
| 7 | Include a Program Review as a potential task for 2012 at the Planning Workshop | Meg Sedlak | To be included in Feb 7th agenda |  |
| 8 | Update SC on lunchtime communication poll from the RMP Annual Meeting. | Rachel Allen | To be included in January 19th SC agenda | To be addressed at January 19th SC meeting |
| 9 | Evaluate coordinating the 2011 RMP Annual Meeting with the State of the Estuary Conference | Meg Sedlak |  | On the agenda for the January SC meeting |

| # | Action Items – August 2010 | Who? | When? | Status 1/11/2011 |
| --- | --- | --- | --- | --- |
| 1 | Speak with Rob Lawrence to encourage more participation by the USACE in the RMP. | Ellen Johnck |  | Sent e-mail to Ellen on this issue |
| 4 | Speak with the USACE about RMP and USACE coordination and funding collaboration. | Ellen Johnck and Rainer Hoenicke |  |  |
| 7 | Send an example of the standard balance sheet to Lawrence Leung and SC members. | Ellen Johnck |  | Sent e-mail to Ellen regarding this issue. |

| # | Action Items – January 2010 | Who? | When? | Status 1/11/2011 |
| --- | --- | --- | --- | --- |
| 5. | Develop a Strategy for Status and Trends | Meg Sedlak | First quarter 2011 | Pending |

| RMP Water Qual represented | MEMBER | Affiliation | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- |
|  |  |  | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q | 1Q | 2Q | 3Q | 4Q |
| POTW-Large | Dave Tucker (1) | City of San Jose | X | P | P | P | X | X | P | P | P | P | - | - |
| POTW-Large | Arleen Navarret (3) | SFPUC | - | - | - | - | - | - | - | - | - | - | P | - |
| POTW-Large | Kirsten Struve (4) | City of San Jose | - | - | - | - | - | - | - | - | - | - | - | P |
| POTW-Med | Dan Tafolla | Vallejo Sanitation and Flood Control District | P | P | P | P | P | P | X | P | X | P | X | P |
| POTW-Small | Ken Kaufman | South Bayside System Authority | X | X | X | X | X | X | X | X | X | X | X | - |
| POTW-Small | Brad Eggleston (5) | City of Palo Alto | - | - | - | - | - | - | - | - | - | - | - | (6) |
| Refineries | Kevin Buchan | WSPA | P | P | P | P | X | (2) | P | P | P | P | P | P |
| Industry | Dave Allen | USS POSCO | P | P | P | P | X | P | P | P | X | P | P | P |
| Cooling Water | Steve Bauman | Mirant Delta, LLC | X | X | X | X | X | X | X | X | X | X | X | P |
| Stormwater | Adam Olivieri | BASMAA (EOA, Inc) | P | X | P | P | P | P | P | P | P | P | P | P |
| Dredgers | Ellen Johnck | Bay Planning Coalition | X | P | P | P | X | X | X | P | P | W* | P | P |
| SF-RWQCB | Tom Mumley | SFB RWQCB | P | P | P | P | P | P | P | P | P | P | P | P |
| SF-RWQCB | Karen Taberski (backup) | SFB RWQCB | - | - | - | - | - | - | - | - | - | - | - | - |
| US Army Corps of Engineers | Rob Lawrence |  | C | X | X | X | X | X | X | X | X | X | X | X |

Notes:

| 1. Dave Tucker elected to SFEI Board, June 2008 | P = present | C = call-in |
| --- | --- | --- |
| 2. Marcus Cole filled in for Kevin Buchan | X = not present | W* = provided input at RMP master planning workshop 4/21/10 |
| 3. Replaced Dave Tucker as Large POTW Rep in May 2010 |  |  |
| 4. Replaced Arleen Navarret as Large POTW Rep in Sep 2010 | - = not a rep at time of meeting |  |
| 5. Replaced Ken Kaufman as Small POTW Rep in Nov 2010 |  |  |
| 6. Karin North filled in for Brad Eggleston |  |  |